## Cable Lenths and Totals
Wire Pulls
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | Use as many as apply
Input | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Demarc | Distance From
Demarc
17.25
| 1.75 | 1.75 | 1.75 | 1.75 | 3.65 | 21.75 | 30 | 11.25 | 14 | 2 | 6.25 | 11.25 | 12 | Distance to first turn
| 16 | 16 | 16 | 16 |  |  | 3 |  | 3.5 |  |  |  | 5.5 | Distance to second turn
| 19.5 | 6.75 | 6.75 | 6.75 | [9 empty] | Distance to third turn
| 7.25 |  | 7 | 8.25 | [9 empty] | Distance to fourth turn
16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | Distance up to attice and down to drop
33.25 | 60.5 | 40.5 | 47.5 | 48.75 | 19.65 | 37.75 | 49 | 27.25 | 33.5 | 18 | 22.25 | 27.25 | 33.5 | Total distance
1 | 2 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 4 | 2 | 4 | 2 | 2 | 34 | # of runs
33.25 | 121 | 162 | 190 | 97.5 | 39.3 | 75.5 | 98 | 54.5 | 134 | 36 | 89 | 54.5 | 67 | 1251.55 | Minimum wire
[14 empty] | 187.7325 | 15% overage
[14 empty] | 1439.2825 | Total Wire Chargeable
The fact that you cannot always pull the specific route you chose in the design, plus the need for "service loop" means you need to have some spare cable in your estimate.
Always pull the longest runs first, to make sure there is still enough in the box to make the following pulls. You don't want to have to buy more than you need.
This Total Wire Chargeable is what you can charge the customer.
The fact that you will be pulling two drops with each run, means that you need either two, 1000 fot boxes, or four 500 ft boxes of wire.
Rationale: Wire is cheaper than paying for the labor to pull the same run twice.

## Pricing
BCIS 3347 Project
Equipment List
Equipment and Components Required
Part | Manufacturer | Description | Cost | Per | Quantity | Total
Router/Modem | NETGEAR | AC 1600 WiFi VDSL/ADSL Modem Router | 114.9 | each | 1 | 114.99
Rack | 1/4 Rack | Wall mount rack | 485 | each | 1 | 485
Patch Panel | Tripp-Lite | 48 port Cat 6 | 153.9 | each | 1 | 153.99
Multiport Switch | HP | 48 Port | 530 | each | 1 | 530
CAT 6e | Plenum | 1000ft roll | 184.9 | each | 2 | 369.8
Patch Cable for Computers | 6ft | 1 per each wall jack | 3.4 | each | 36 | 122.4
Patch Cable for patch panel | 2ft | 1 per each wall jack | 2.75 | each | 18 | 54
Multi port Wall Plates | White | 2 per room | 5 | each | 18 | 90
UPS | Tripp-Lite/APC | 15 minute | 275 | each | 1 | 275
Firewall | RATtrap | Smart Internet security Firewall | 199 | each | 1 | 199
WAP | Cisco | Cisco AIR contoller based Wireless Access Point | 260 | each | 1 | 260
J hooks / ladder rack | 50 pack | 1 per 3 ft of pulled wire | 2.84 | pack | 2 | 5.68
Extension Board | Amazon | Power Strip | 8.99 | each | 1 | 8.99
0
[5 empty] | Sub total parts | 2668.85
|  |  |  | State Tax | 0.0825 | 220.1801
[5 empty] | Total Parts | 2889.0301
Labor
Application | Description |  | Cost | Per | Quantity | Total
Cable Installation | Pull cable from DeMarc to all over the apartment |  | 80 | pull | 36 | 2880
Rack installation | Install and test all wall rack |  | 150 | hour | 4 | 600
[5 empty] | Total Labor | 3480
Total Cost |  |  |  |  | Total Proposal | 6369.0301
Recurring Expence
Service | Vendor/
Name | Manufacturer | Description | Cost | Unit | Quantity | Total
Internet Connection | CenturyLink/AT&T/Spectrum etc. | Telco DSL/Cable DSL/Wireless/SatCom speed each direction | 89.89 | Month | 1 | 89.89
ISP Connection Device | Netgear/Cisco/HP | DSL modem/router, Switch, WAP | 9.75 | Month | 1 | 9.75
[5 empty] | Total Monthly | 99.64
[5 empty] | Total Annual | 1195.68

## Timeline
Timeline | [8 empty] | On Site
Inclusive dates
| Order Delivery Date | [5 empty] | Weekend | [6 empty] | Weekend
Preliminary walk-through | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04 | 2019-04-05 | 2019-04-06 | 2019-04-07 | 2019-04-08 | 2019-04-09 | 2019-04-10 | 2019-04-11 | 2019-04-12 | 2019-04-13
Hardware Cost Received | 2019-03-25: 2019-03-25
Order Parts
CAT 6e UTP wire | 2019-03-25: 2019-03-25
Patch Panel | 2019-03-25: 2019-03-25
Rack | 2019-03-25: 2019-03-25
Wall Jacks | 2019-03-25: 2019-03-25
J hooks | 2019-03-25: 2019-03-25
cat 6e patch cable 2ft | 2019-03-25: 2019-03-25
cat 6e patch cable 6ft | 2019-03-25: 2019-03-25
Router/Modem
Parts Delivered
Wire Installation
Pull wire | bar: 2019-03-28 to 2019-03-30
Terminate Boxes | bar: 2019-03-28 to 2019-03-30
Order Parts
Switch | 2019-03-25: 2019-03-25
UPS | 2019-03-25: 2019-03-25
Extension board | 2019-03-25: 2019-03-25
WAP's | 2019-03-25: 2019-03-25
Firewall | 2019-03-25: 2019-03-25
Router/Modem | 2019-03-25: 2019-03-25
Rack Installation
Mounting Pack | bar: 2019-04-02 to 2019-04-06
Add Patch Panel to Rack | bar: 2019-04-02 to 2019-04-06
Punch Down Rack | bar: 2019-04-02 to 2019-04-06
Add Rack Components | bar: 2019-04-02 to 2019-04-06
Walk Trhough | bar: 2019-04-09 to 2019-04-11
PunchList Start | bar: 2019-04-09 to 2019-04-11
Final Walkthrough | bar: 2019-04-09 to 2019-04-11
Complete | bar: 2019-04-12 to 2019-04-13